## Tabelle1
Page	Requested change	Comment	Work Category	Status
General
All pages top right	Please change "Allergolgie" to "Allergologie / Allergologie select"		Development	Pending
All pages left bar	Please change "Imprint" to "Legal Notice"		Development	Pending
http://typo3.p621956.webspaceconfig.de/welcome	Please change "Welcome to the manuscript submission site of Allergologie" to "Welcome to the manuscript submission site of Allergologie / Allergologie select"		Development	Pending
All pages that show the list of manuscripts	Would it be possible to make the red/green bar at the left broader so that it's easier to see whether the manuscript is Active or in the Archive? / On smaller screens, the bar is only visible in every second manuscript	Screenshot 9 / Screenshot 10	Design	Done

Editor account
After log in of Editor	Please show page "Editors zone" -> "Active Manuscripts"		Development	Pending
http://typo3.p621956.webspaceconfig.de/statistics	Wow, really cool! But this page might need a bit of further fine tuning, e.g. it would be great to define time periods, like "all time" or "2024". Could we do that at a later step, as it also does not make too much sense in Allergologie, where we don't have Section Editors		Development	Pending
http://typo3.p621956.webspaceconfig.de/editors-zone/active-manuscripts	Only on smaller screens (or when in portrait format): Links can only be clicked on a few pixels, i.e., not the whole button is working as a link	Screenshot 1	Design	Done
"Manuscript details" pages	Please change heading to "Manuscript Details" (plural)		Development	Pending
"Manuscript details" pages	Please allign right column	Screenshot 2	Development/Design	Pending
"Manuscript details" pages	The left column could be much smaller so we would have more place for the texts in the right column (particularly important on smaller screens)	Screenshot 2	Design	Done
In general	Would be great if everything that can be clicked would be visible buttons	example in Screenshot 3	Development	Pending
"Manuscript details" pages	The reviewer ratings are difficult to see, and the buttons "Release" and "Upload and Release Modified Review for Author" are missing	Sreenshot 4	Development/Design	Pending
Reviewer invitations page	Could this page be adapted to the new overall style better? Like blue buttons and so on? In general, it would be great if it could look more "modern".		Discussion	Pending
Reviewer invitations page	Specialties do not correspond to what is currently in the system. It should be: Basic research; Basic research, allergen characterization; Dermatology; Drug allergies; Environmental allergies; Epidemiology; Food allergies; Immunology; Occupational allergies; Pediatric allergology; Respiratory allergies, lower airways (incl bronchial asthma); Respiratory allergies, upper airways (incl rhinitis)		Development	Pending
Reviewer invitations page	When reviewers are shown, their statistics are no longer shown. / What's most important is some kind of coding for "unreliable" to "very reliable" depending on the reviewers' invitation-to-posted ratio.	Please check screenshot 5 to see how it should be	Development	Pending
Reviewer invitations page	When I use "Search User", their specialties are not shown.		Development	Pending
http://typo3.p621956.webspaceconfig.de/editors-zone/active-manuscripts	I think, the extra buttons to send reminders are superfluous, because we can already send reminders using the "Status" button; maybe we should simply rename the button "Status" to "Status/Reminders".	Screenshot 6	Development	Pending
Reviewer Status page	It would be great if we could put the buttons to send a reminder or stop a reminder below the columns. In addition, could you please introduce a third option: "Uninvite reviewer" as we currently have it in the Clinical Nephrology OSSY?	Screenshot 7	Development/Design	Pending
In "Archive Manuscripts"	What does the status "Approved" mean? We did not have this before, and I don't even know how I would change a manuscript's status to "Approved".		Development	Pending

Reviewer account
/	/	Everything looks fine!

Author account
Galley proofs link/button	Would it be possible to hide the button/link until further notice?	Great that you already introduced this! But we would need a "counterpart", i.e., some account where we could upload the galley proofs. This would be the account "Publisher", which we currently don't have (if I'm not mistaken). / We will have to work out the entire process (including email templates and so on). We'll have to do that separately	Development	Pending
Galley proofs	When we introduce the galley proof option: / • There will have to be another button called "Download galley proofs", and the button "Upload galley proofs" has to be renamed to "Upload corrections". / • It is very important that the author cannot upload corrections or forms before the publisher has uploaded the galley proofs.	Screenshot 8	Development	Pending